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NHS Finance Insights Placement Scheme 2027
Timeline 

	September 2026
	Engagement begins – internal and external 

	September onwards 2026
	School and college visits take place – candidates 
can register their interest via the website

	October 2026
	National Webinar for organisations

	December 2026
	All organisations confirmed and MOU completed 
by COP 18th December – Hard deadline
Application form created and live on the website before the Christmas break

	January 2027
	Applications officially open 1st January  

	March 2027
	National Webinar & Placement Manager training

	April 2027
	Central team check in with current applicants if 
still interested

	May 2027
	Applications close (7th May), organisations must
pull out before applications close if they do not 
want to be involved anymore (30th April).

	Mid – May 2027
	National team initial shortlist. Contact 
unsuccessful applicants and confirm with those 
who are through to the next stage when they 
should expect a response.

	End May / early June 2027 
	Regional Shortlisting of applications and checking shortlisted candidates against scheme criteria. 

	Mid - June 2027
	Notify shortlisted candidates

	End of June / early July 2027
	Interviews to take place and references are 
collected 

	Mid July 2027
	Confirm success candidates and match with host

	Mid July – August 2027
	Hosting organisations complete HR enrolment processes 

	September 2027
	Placement begins 

	September 2027
	National induction 1

	September 2027
	National induction 2 

	End September / October 2027
	Regional inductions day (Region’s decision)


	February 2027
	National development day 1 – Online 

	June 2027
	National development day 2 – Online 

	July / August 2027 
	Central team to circulate feedback to Students 
and managers

	September 2027
	Placement ends – circulate certificate 
Regional send-off (Region’s decision)
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