NHS Finance Insights Placement Scheme 2027

Timeline

| September 2026 | Engagement begins – internal and external |
| --- | --- |
| September onwards 2026 | School and college visits take place – candidates can register their interest via the website |
| October 2026 | National Webinar for organisations |
| December 2026 | All organisations confirmed and MOU completed by COP 18th December – Hard deadline Application form created and live on the website before the Christmas break |
| January 2027 | Applications officially open 1st January |
| March 2027 | National Webinar & Placement Manager training |
| April 2027 | Central team check in with current applicants if still interested |
| May 2027 | Applications close (7th May), organisations must pull out before applications close if they do not want to be involved anymore (30th April). |
| Mid – May 2027 | National team initial shortlist. Contact unsuccessful applicants and confirm with those who are through to the next stage when they should expect a response. |
| End May / early June 2027 | Regional Shortlisting of applications and checking shortlisted candidates against scheme criteria. |
| Mid - June 2027 | Notify shortlisted candidates |
| End of June / early July 2027 | Interviews to take place and references are collected |
| Mid July 2027 | Confirm success candidates and match with host |
| Mid July – August 2027 | Hosting organisations complete HR enrolment processes |
| September 2027 | Placement begins |
| September 2027 | National induction 1 |
| September 2027 | National induction 2 |
| End September / October 2027 | Regional inductions day (Region’s decision) |
| February 2027 | National development day 1 – Online |
| June 2027 | National development day 2 – Online |
| July / August 2027 | Central team to circulate feedback to Students and managers |
| September 2027 | Placement ends – circulate certificate Regional send-off (Region’s decision) |